## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E003A |  | Project Name: |  | Cottonwood Classical Academy
NPDES Id. No. | NMR1004DU |  | Location: |  | 7800 Jefferson St NE
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Cottonwood Classical Foundation |  |  |  | Inspections Plus
Contact name & title |  | John Binnert
e-mail |  | john.binnert@cottonwoodclassical.org
Contact Phone # |  | 505-998-1021 |  |  |  | 505-344-9410
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 2 |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The required NPDES posting was missing/removed. Until the site is Determined Stabilized by the City, you must comply with the conditions of the CGP. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5.
2 | The west portion of your site has large areas of bare dirt without any BMPs or stabilization and one or the other is required. The stockpile wasn't shown on either the Grading Plan or the approved ESC Plan and doesn't meet typical limitations for stockpiles. The approved ESC Plan didn't show any land disturbing activity where the stockpile is located, so the stockpile area must be added to an updated SWPPP map with finished grades approved by Hydrology,and BMPs (Silt-fence) around the perimiter of the new limits of disturbance. It must be graded according to the approved grading plan while protected by the BMPs shown on your up-to-date SWPPP map then stabilized per Part 2.2.14.c. "You may terminate CGP coverage only if one or more of the conditions in Parts 8.2.1, 8.2.2, or 8.2.3 has occoured." Then request a Stabilization Determination from the City in order to discontinue self inspections in accordance with City Ordinance § 14-5-2-11(C)(1).
3 | An up-to-date SWPPP and reports were unavailable at the time of inspection. The CGP coverage has expired, therefore the SWPPP does not include a current and active NOI. Section 7.1 states that you must develop and update a SWPPP throughout coverage and ensure that it meets the current 2022 CGP requirements. Section 7.3 states that you are required to keep a current copy of the SWPPP on-site or easily accesible so that it can be made available for inspections. The City of Albuquerque ordinance requires that self inspections continue until the city determines the site stabilized. Renew the NOI and update the SWPPP map to include all disturbed areas, including the stockpile and continue self inspections. The SWPPP must be up-to-date and available onsite.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date:
Notes:
No prior inspections performed, construction activity seems to have ceased and all BMPs have been removed. There are still stockpiles and distrubed land that are not stabilized. The NOI is expired.
| City of Albuquerque Stormwater Inspector Signature and date: | [5 empty] | 2023-06-16
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action