## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E074 |  | Project Name: |  | Ellison St Office Warehouse
NPDES Id. No. | NMR1004CM |  | Location: |  | 4000 Ellison St NE
2024-10-22 |  | Owner |  |  |  | Contractor
Operator |  | Security Self Storage, LLC |  |  |  | Mechenbier Construction, Inc.
Contact name & title |  | Jeremy J. Mechenbier |  |  |  | Jeremy J. Mechenbier
e-mail |  | jeremymechenbier@mechenbier.com |  |  |  | jeremymechenbier@mechenbier.com
Contact Phone # |  | 505-314-7700 |  |  |  | 505-314-7700
COA Inspector |  | Chancellor English |  |  |  | Time |  | 1:30pm |  |  |  | Rain
Construction Phase: |  | Inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2024-10-14
Notes:
The SWPPP was at Mechenbier Construction, a few blocks away, so the City met with J. Mechenbier at the office. The outfall showed no signs of discharge and no erosion at the outlet. A block wall has been installed on the eastern, southern, and western perimeter. Most discharge settles into the middle of the site from excavation/grading. No signs of sediment discharge from recent storm activity.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action