## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Legacy @ Journal Center
Location: |  | 5151 Lang |  |  |  | ESC File No. | D17E106 |  | NPDES Id. No. | NMR1000DI
Site Contact Name & Agency |  | Brian Paterson |  |  |  | Phone: (o) | NMR10007S
[6 empty] | Phone: (m) | 505-998-0163
Owner |  | Titan |  |  |  | Phone: (o)
Owner's e-mail |  | bpatterson@titan-development.com |  |  |  | Phone: (m) | 505-998-0163
Inspection Date: |  | 2020-09-15 | Start/End Time: |  | 12noon | [7 empty] | Partly Cloudy
CoA Stormwater Inspector: |  |  | Doug Hughes | [9 empty] | Rain
Construction Phase: |  | inactive graded sites | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2020-10-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Siltfence repaired
2 | hydromulch applied to all disturbed areas
3
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  | n/a |  | Latest report Date: |  | n/a
Notes: | Inspection conducted adhering to Covid-19 constraints
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes - 924-3420
|  | jhughes@cabq.gov |  |  |  |  | 2020-09-15

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action