## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E106 |  | Project Name: |  | Legacy @ Journal Center
NPDES Id. No. | NMR1007S |  | Location: |  | 5001 Lang Ave. NE | [5 empty] | nmr12bj67
2021-05-07 |  | Owner |  |  |  | Contractor
Operator |  | Titan Development
Contact name & title |  | Brian Patterson
e-mail |  | bpatterson@Titan-Development.com
Contact Phone # |  | 505-998-0163
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 8:25 AM/8:30 AM |  |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 68 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | Section of silt fence on the East side is nearly gone. Replace this section of silt fence and continue maintenance. | [8 empty] | 2021-05-03
2 | No posting of permit. Post signage of permit coverage in location that is visible to the public.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | No activity on site. Small dirt piles along West boundary of site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action