## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E107 |  | Project Name: |  | Legacy 2 @ Journal Center
NPDES Id. No. | NMR1003FK |  | Location: |  | 7800 Headline Blvd NE
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Titan Development LLC |  |  |  | Pavilion Construction
Contact name & title |  | Joshua Rodgers |  |  |  | Keven Mohundro
e-mail |  | jrogers@titan-development.com |  |  |  | kmohundro@pavilionconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-218-1023
COA Inspector |  | Chancellor English |  |  |  | Start/End Time | 2pm |  |  |  | Rain
Construction Phase: |  | CO | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Materials storage and waste dumpster lacked cover at the time of inspection. You must minimize the exposure to precipitation and minimize the discharge of pollutants in accordance with the requirements of CGP Section 2.3.3
2 | Permit coverage expired in 2022. Resubmit NOI for the current CGP. An up-to date SWPPP was not available for the inspection. The storage area and dumpster were not marked on the ESC Plan submitted to the city and no SWPPP map to check if that map had been updated. Please provide a renewed NOI and ensure SWPPP is up to date.
In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date:
Notes: | One prior violation for BMP maintenance in 2021
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action