## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E107 |  | Project Name: |  | Allaso Journal Center
NPDES Id. No. | NMR1003FK |  | Location: |  | 7800 Headline Blvd. NE |  |  |  |  | Bob Kearney
2021-05-07 |  | Owner |  |  |  | Contractor |  |  |  | bkearney@titan-development.com
Operator |  | Titan Development |  |  |  | Pavilion
Contact name & title |  | Joshua Rogers |  |  |  | Kevin Mohundro
e-mail |  | jrogers@titan-development.com |  |  |  | kmohundro@pavilionconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-218-1023
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 9:00 AM/9:25 AM |  |  |  | Rain
Construction Phase: |  | Earthwork | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 68 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | Soil accumulation higher than one half the height of the silt fence in the SW corner. Remove accumlated soil from the silt fence. | [8 empty] | 2021-05-03
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Water trucks and tank on site. Work began in early March.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action