## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D17E112 |  | Project Name: |  | Allaso JC-Six Apartments
NPDES Id. No. | NMR1005DB |  | Location: |  | 7501 Jefferson St. NE
2024-06-24 |  | Owner |  |  |  | Contractor
Operator |  | Titan JC6 LLC |  |  |  | HB Construction
Contact name & title |  | Josh Rogers |  |  |  | Zach Gruen
e-mail |  | jrogers@titan-development.com |  |  |  | zachg@hbconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 505-856-0404
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 100 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-10 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-06-11
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action