## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D18E009 |  | Project Name: |  | Hope Christian High School Phase 1
NPDES Id. No. | NMR1006FW |  | Location: |  | 6800 Palomas Ave NE
2024-07-24 |  | Owner |  |  |  | Contractor
Operator |  | Hope Christian Schools, Inc. |  |  |  | PWKI, LLC
Contact name & title |  | Teressa Groom |  |  |  | Paul Kenderdine
e-mail |  | tkgroom@hcsnm.org |  |  |  | pwki.llc@gmail.com
Contact Phone # |  | 505-263-7540 |  |  |  | 505-867-1765
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | Utilities, grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-21 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was not certified by the operators in violation of CGP Part 7.2.10. The self-inspection reports were not able to be viewed on-site during the inspection in violation of CGP Part 4.7.3. The SWPPP Map has not been amended to show the current on-site conditions (relocated construction exit) in violation of CGP Part 7.4.1. Required mitigation: Your signatory must sign and date your SWPPP in accordance with CGP Appendix G, Part G.11, as per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that they can be made immediately available at the time of inspection per CGP Part 4.7.3. You must modify your SWPPP, including the site map(s) whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.
2 | BMPs - There are gaps in the silt fencing on the south side of the site adjacent to the arroyo in violation of CGP Part 2.1.4. The construction exit has no track-out controls in violation of CGP Part 2.1.3. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4. Complete installation of stormwater controls by the time each phase of construction activities has begun per CGPO Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | 2024-07-22
Notes:
The SWPPP was located with the superintendent in his truck.
Sediment track-out was evident, but not major at this time - this will need to be swept up.
There is sediment build-up at the outfall on the west side of the property with enough to discharge sediment from the construction area of the property.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action