## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D18E009 |  | Project Name: |  | Hope Christian High School Phase 1
NPDES Id. No. | NMR1006FW |  | Location: |  | 6800 Palomas Ave NE
2025-06-11 |  | Owner |  |  |  | Contractor
Operator |  | Hope Christian Schools, Inc. |  |  |  | PWKI, LLC
Contact name & title |  | Teressa Groom |  |  |  | Paul Kenderdine
e-mail |  | tkgroom@hcsnm.org |  |  |  | pwki.llc@gmail.com
Contact Phone # |  | 505-263-7540 |  |  |  | 505-867-1765
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP was not certified by the owner (Hope Christian Schools, Inc.) in violation of CGP Part 7.2.10. The inspection reports were missing from the site in violation of 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP and self-inspection reports in accordance with CGP Appendix G, Part G.11, as per CGP Part 7.2.10. You must keep a copy of all inspection reports at the site or at an easily accessible location so they can be made immediately available during the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Retaining wall prevents discharge off property and into a pond.
The superintendent was not located during the inspection to ask about the reports.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action