## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D18E009A |  | Project Name: |  | Hope Christian Elementary School
NPDES Id. No. | NMR1002NC |  | Location: |  | 6801 Palomas
2021-07-07 |  | Owner |  |  |  | Contractor
Operator |  | Hope Christian School |  |  |  | PWKI
Contact name & title |  | Teresa Groom |  |  |  | Adam Kenderdine
e-mail |  | tkgroom@hcsnm.org |  |  |  | adam@pwki.com
Contact Phone # |  | 505-821-2513 |  |  |  | 505-908-5066
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 8:55 AM-9:05 AM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 81 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-07-06 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Areas not stabilized on North side. Sediment is washing out on to the concrete pad. Need to stabilize this area per CGP 2.2.14.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-05-12
Notes: | South side is stabilized.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action