## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Santa Monica Estates II
Location: |  |  | Brentwood Blvd & Santa Monica
Site Contact Name & Agency |  |  | Abrazo Homes |  |  |  | ESC File No. | D18E054E_A
|  |  | chris@abrazohoomes.com |  |  |  | NPDES Id. No.
Inspection Date: |  |  | 2020-01-15 | Start/End Time: |  | 0730/074hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | home construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | X | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 31* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2019-11-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Please provide NPDES posting of the site.
2 | Please provide approval of the ESC plan to City Storm Water Quality program.
3 | Domestic and Construction waste not in acceptable container. Please clean and use the provided
refuse containers.
4 | Washouts not in acceptable washout container or faciilty. Please mitigate and prevent in the future.
5 | Please provide the latest SWPPP self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  | requested |  | Latest report Date: |  | 2019-11-11
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2020-01-15

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action