## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Overture Senior Active Adult
Location: |  | 6441 Palomas
Site Contact Name & Agency |  | Clay - Pavillion |  |  |  | ESC File No. | D18E056A
|  | cgriffin@pavilionconstruction.com |  |  |  | NPDES Id. No. | NMR1001Q2
Inspection Date: |  | 2019-12-11 | Start/End Time: |  | 0830/0845hrs
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  | Plumbing, wall building | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 31* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [8 empty] | 2019-11-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
all previous issues mitigated, no new issues observed with this inspection
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2019-12-09
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2019-12-11

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action