## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | D19E031 |  | Project Name: |  | Palomas Peak Phase 2
NPDES Id. No. | NMR1002QI |  | Location: |  | 8310 Palomas Ave. NE
2021-04-06 |  | Owner |  |  |  | Contractor
Operator |  | Palomas Peak, LLC.
Contact name & title |  | Eric Tidmore
e-mail |  | eric@trinitynm.com
Contact Phone # |  | 505-830-1928
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:45 PM/2:30 PM |  |  | Rain
Construction Phase: |  | Grading | [8 empty] | Clear/ Windy
Type of Inspection: |  | Follow Up |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 70 |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Silt fence needs to repaired or replaced
2 | Concrete washout needs to be removed and disposed.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-07-20
Notes: | Vehicles are parking on the west lot. No construction activity. Need latest inspection
report. NPDES permit sign is posted in East lot.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action