## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E10E079 |  | Project Name: |  | Dorado Montano Townhouses
NPDES Id. No. | NMR10039I |  | Location: |  | 5915 Golden Avenue NW
2023-04-10 |  | Owner |  |  |  | Contractor
Operator |  | GR Real Investments, LLC. |  |  |  | Tir Burch Development, LLC.
Contact name & title |  | Greg Lobberegt |  |  |  | Ahmet Tiryaki
e-mail |  | greg@greglobb.com
Contact Phone # |  | 505-269-4734 |  |  |  | 615-4278
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 11:25 AM/11:40 AM |  |  |  | Rain
Construction Phase: |  | Earthwork | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | The Final Stabilization Criteria CGP2.2.14.c has been satisfied. Now you must send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP. This step is independent of the Certificate of Occupancy. Please copy me with the documentation and the EPA’s acceptance of the NOT. | [8 empty] | 2021-05-03
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date:
Notes:
CGP Coverage Expired and still needs terminated
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action