## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E11E013B |  | Project Name: |  | Saranam Housing
NPDES Id. No. | NMR1004MQ |  | Location: |  | 4701 Montano Rd NW
2024-08-23 |  | Owner |  |  |  | Contractor
Operator |  | Saranam, LLC |  |  |  | Eco Terra LLC
Contact name & title |  | Tracy Weaver |  |  |  | Michael Cecchini
e-mail |  | tweaver@saranamabq.org |  |  |  | mike@ecoterrallc.com
Contact Phone # |  | 505-299-6154 |  |  |  | 505-918-8476
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2PM |  |  |  | Rain
Construction Phase: |  | Placement of pre-fab houses | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were not located during the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep an up-to-date copy of your SWPPP and a copy of all your self-inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. Ensure that the SWPPP and all inspection reports are certified by all operators persuant to CGP Appendix G, Part G.11.
4 | Discharge off site? (Y/N) |  |  | no | Latest report Date: |  | 2023-07-10 |  |  |  | no
Notes: | The SWPPP was previously held in the original "family" room/building on-site. The SWPPP was not found during the current inspection.
This site slopes toward Montano Rd, but a newly graded ditch is supposed to intercept drainage and pipe it into an on-site duck pond. If that works, there shouldn't be very much discharge to Montano Rd. No sediment discharged from this site was present in Montano Rd.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action