## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E11E013B |  | Project Name: |  | Saranam Housing
NPDES Id. No. | NMR1004MQ |  | Location: |  | 4701 Montano Rd NW
2024-03-25 |  | Owner |  |  |  | Contractor
Operator |  | Saranam, LLC |  |  |  | Eco Terra LLC
Contact name & title |  | Tracy Weaver |  |  |  | Michael Cecchini
e-mail |  | tweaver@saranamabq.org |  |  |  | mike@ecoterrallc.com
Contact Phone # |  | 505-299-6154 |  |  |  | 505-918-8476
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 10AM |  |  |  | Rain
Construction Phase: |  | Interior and exterior finish on first three pre-fab houses | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP certification wasn't signed in violation of CGP Appendix G 11.2, and the latest self-inspection reports were missing. The SWPPP Team member's responsabilities per CGP 6.1 and the individuals are not identified in Violation of CGP 7.2.2. The SWPPP incorrectly says Tiera West is the inspector, but reports are by E2RC. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3.
2 | BMPs need to be maintained per CGP 2.1. The trackout pad was full of sediment and needed reset. Required mitigation: If at any time you find that a stormwater control needs routine Maintenance, you must immediately initiate the needed maintenance work and complete such work by the close of the next business day. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete the repair by no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
4 | Discharge off site? (Y/N) |  |  | no | Latest report Date: |  | 2023-07-10 |  |  |  | no
Notes: | The SWPPP was in the original "family" room/building on-site.
This site slopes toward Montano Rd, but a newly graded ditch is supposed to intercept drainage and pipe it into an on-site duck pond. If that works, there shouldn't be very much discharge to Montano Rd. No sediment discharged from this site was present in Montano Rd.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action