## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | O'Reilly's Auto Parts
Location: |  | 6380 Coors (Coors & La Orilla)
Site Contact Name & Agency |  | Robert Duncan - HuttonExchange |  |  |  | ESC File No. | E12E006G
|  | rduncan@huttonbuild.com |  |  |  | NPDES Id. No. | NMR1001Dt
Inspection Date: |  | 2019-05-15 | Start/End Time: |  | 9:50/10:25
CoA Stormwater Inspector: |  |  | Curtis Cherne | [8 empty] | Rain
Construction Phase: |  | vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  | 311/Complaint | X | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-05-10 |  |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Numerous washouts through out the site
2 | Costruction Wastes not in an acceptable container
3 | Construction site waste(s) on adjoining properties
4 | Dirt ramp to let to the east with no sediment BMP
5 | No acceptable wash-out facility onsite
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  | request |  | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Curtis Cheren PE 505-924-3420
|  | ccherne@cabq.gov |  |  |  |  | 2019-05-15

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action