## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E12E015G |  | Project Name: |  | Overture Andulacia |  |  |  |  | 'nwhittaker@greystar.com'
NPDES Id. No. | NMR1003QM |  | Location: |  | 5301 Antequera Rd. NW
2021-05-12 |  | Owner |  |  |  | Contractor |  |  |  | 'Sydney Fetter' <sfetter@e2rc.com>
Operator |  | CRP-GREP Overture Andulacia, LLC |  |  |  | Pavilion Construction
Contact name & title |  | Nic Whittaker |  |  |  | Joseph Aguilar
e-mail |  | nwhittaker@greystar.com |  |  |  | jaguilar@pavilionconstruction.com |  |  |  | jaguilar@pavilionconstruction.com
Contact Phone # |  | 512-762-2473
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 12:25 PM/12:40 PM |  |  |  | Rain
Construction Phase: |  | earthwork | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 72 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | Sediment in the street and near inlet. Remove sediment from the streets daily. | [8 empty] | 2021-05-03
2 | Missing sediment control BMP on a section of the East perimeter. Install BMP to prevent sediment from entering the streets.
Yes
2.1 | Discharge off site? (Y/N) |  |  | yes | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Earthwork began on 5/3/2021. Water has pooled around the inlet. The wattle is providing
good protection. Recommend grading the pond in the NE corner as an early BMP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action