## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E17E004 |  | Project Name: |  | Power Motive Corporation
NPDES Id. No. |  |  | Location: |  | 6101 Pan American Freeway NE
2023-08-23 |  | Owner
Operator |  | PMC Albuquerque, LLC.
Contact name & title |  | Nick Kirkpatrick
e-mail |  | nkirkpatrick@powermotivecorp.com
Contact Phone # |  | 505-345-8383 & 303-355-5900
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: | 10:00 |  |  |  | Rain
Construction Phase: |  | Grading Dirt | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  | 85 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-08-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI missing - Construction Activities are taking place without coverage under the EPA's Construction General Permit (CGP) in violation of CGP 1.1. The site is used to store construction equipment for rent and for sale. Construction equipment maintenance also occurs onsite. Occasionally the equipment is tested/demonstrated by moving dirt around (grading). Vegetative cover was removed many years ago. The City approved a Drainage Report for this 10 acre site on 7/22/1976. Google earth photes dating back to 1994 show about 4 acres of land disturbance on this site for the last 30 years or more. Most of the rest of this site is covered by buildings and pavement. Appendix A of the EPA's CGP defines “Construction Activities” – earth-disturbing activities, such as the clearing, grading, and excavation of land, and other construction-related activities (e.g., grubbing; stockpiling of fill material; placement of raw materials at the site) that could lead to the generation of pollutants." Required mitigation: A Storm Water Pollution Prevention Plan (SWPPP) must be prepared by a Qualified Erosion Control Specialist who will then help you file your Notice of Intent (NOI) with the EPA. You must then submit your NOI, ESC Plan, application form (attached), and fees to the City Stormwater Quality (SWQ) Section for approval.
2 | Posting was missing
3 | SWPPP and inspection reports were missing
4 | BMPs were missing
2 | A sediment laden stormwater discharge occoured from this site during the storm on 8/8/23 causing sediment accumulations of up to 3" depth for a distance of about 150' on the east side of Jefferson Street. adjacent to the northwest corner is this site as noted during a city driveby inspection on 8/9/23. The property owner, PMC Albuquerque, LLC., has not filed a Notice of Intent (NOI) to use the EPA's Construction General Permit (CGP). Permit coverage for such stormwater discharges has been required since the effective date of the first CGP effective October 1, 1992 even if the construction activities comenced befor the permit went into effect. City street mantenance was in the process of removing the sediment during a second driveby inspection on 8/23/23. Required Mitigation:
2.1 | Discharge off site? (Y/N) |  |  | Yes | [5 empty] | Yes
4 | Self Inspection Reports |  |  | no | Latest report Date:
Nick Kirkpatrik at the corporate office in Denver is the Director of Facuilities for Power Motive Corp. a parent company of PMC Albuquerque LLC. nkirkpatrick@powermotivecorp.com at 970-778-1826
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action