## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E17E011B |  | Project Name: |  | XRANM
NPDES Id. No. | NMR1004F0 |  | Location: |  | 5800 Jefferson St NE
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Jefferson 25 XRANM QOZB, LLC |  |  |  | Enterprise Builders
Contact name & title |  | Jeff Jesionowski |  |  |  | David Lundsten
e-mail |  | jeff@amcdevelopment.com |  |  |  | dlundsten@ebnm.com
Contact Phone # |  | 259-0991 |  |  |  | 452-7639
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | infrastructure complete northern lot not stable | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The lot north of the construction area is not stabilized. The City received an amended ESC plan to include this northern lot on the map which includes instructions to stabilize it using 2" of pit run gravel. Install and place gravel to have no bare soil spots to stabilize the northern lot or provide stabilization that satisfies one of Parts 8.2.1, 8.2.2, or 8.2.3 of the CGP.
2 | In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | 2023-03-28
Notes:
Previous violations are outdated SWPPP, Washout, and Waste disposal. Stabilization of the northern lot has been added to ESC Plan and an infromal violation issued for stabilization not being in place.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action