## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E19E025C2 |  | Project Name: |  | Dutch Bros Coffee NM0504
NPDES Id. No. | ESC Permit |  | Location: |  | 7330 San Antonio Dr NE
2025-11-24 |  | Owner |  |  |  | Contractor
Operator |  | Dutch Bros Coffee/MDG Real Estate |  |  |  | Wilger
Contact name & title |  | Ron Austerman |  |  |  | Jared Stanford
e-mail |  | ron.austerman@dutchbros.com |  |  |  | jstanford@wilger.com
Contact Phone # |  | 602-320-8598 |  |  |  | 505-850-3706
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | Foundation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-23 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - There were no self-inspection reports available during the inspection in violation of City Ordinance §14-5-2-11. Required mitigation: City Ordinance §14-5-2-11 (C)(1) states "At a minimum, a routine compliance self-inspection is required to review the project for compliance with the Construction General Permit once every 14 days and after any precipitation event of 1/4 inch or greater until the site has been completed and the site determined as stabilized by the city. Reports of these inspections shall be kept by the person or entity authorized to direct the construction activities on the site and shall be conducted during progress of the work, during work suspensions, and until final acceptance of site stabilization by the city."
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | NA
Notes:
ESC Permit only, no need for SWPPP or NOI.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action