## 04.2019Form
|  | City of Albuquerque ---Stormwater Construction Site Inspection Report--- | [8 empty] | Weather: | Discharge: | Reports: | ROW:
General Information | [11 empty] | Shadow | Yes
ESC File # | E19E025C2 |  | Project Name: |  |  | Dutch Bros Coffe NM0504 | [5 empty] | Yes | No
NPDES ID # | ESC Permit |  | Location: |  |  | 7330 San Antonio Dr NE | [5 empty] | No | Requested | Sidewalk
2026-02-26 |  | Owner |  |  |  |  | Contractor |  |  |  | Snow |  | Out-of-date | Street
Operator |  | MDG Real Estate |  |  |  |  | Wilger |  |  |  | Clear |  | Unsigned | Storm Drain Inlet
Contact name & title |  | Ron Austerman |  |  |  |  | Jared Stanford |  |  |  | Rain |  |  | Drainage Ditch
Contact e-mail |  | ron.austerman@dutchbros.com |  |  |  |  | jstanford@wilger.com |  |  |  | Clear/Windy |  |  | Arroyo
Contact Phone # |  | 602-320-8598 |  |  |  |  | 505-850-3706 |  |  |  | Windy |  |  | Private Property
COA Inspector |  | Chancellor English |  |  |  |  | Start/End Time: |  | 10:30am |  | Cloudy |  |  | N/A
Construction Phase: |  | Verticals, curbing | [8 empty] | Sleet
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up
Weather at time of inspection: |  |  |  | Clear |  | Temperature: ~ |  | 65
Estimated date of last storm 0.25" or greater: |  |  |  |  | 2026-01-08
Item Number | Deficiency/ Corrective Action
1 | None
Discharge off-site? |  | No | Right-of-way: |  |  | N/A
Self-Inspection Reports? |  | Yes | Latest report Date: |  |  | 2026-02-17
Notes:
Inspection reports are in the construction office; no SWPPP or NOI required.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action