## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E22E002 |  | Project Name: |  | Albuquerque Ranch Estates II
NPDES Id. No. | NMR1004JQ |  | Location: |  | Vic Royal Oak St & McKay Way NE
2024-04-30 |  | Owner |  |  |  | Contractor
Operator |  | 505 Solutions, LLC
Contact name & title |  | Rachel Bevan
e-mail |  | rachelbevan06@gmail.com
Contact Phone # |  | 505-269-1418
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  | Rain
Construction Phase: |  | none, weeds and partial land disturbance | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | NOI - The permit coverage has been terminated, but it appears that there is no final stabilization in violation of City Ordinance 14-5-2-11. Required mitigation: For projects that disturb one acre or more, or less that one acre but are part of a larger common plan of development, the property owners is to provide the CGP eNOI documentation that contains the property owners' names and contact information a minimum of 14 days prior to earth disturbance per City Ordinance 14-5-2-11(A).
Posting - The permit coverage posting has been removed in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5.
SWPPP - The SWPPP and self inspection reports were not onsite in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and copies of all inspection reports at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your site per CGP Part 7.3.
BMPs - The stormwater controls for the disturbed areas have been removed in violation of CGP Part 2.2.3. Required mitigation: Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3.
Stabilization: The disturbed areas have not been stabilized in accordance with the schedule requirements listed in CGP Part 2.2.14 and Permit coverage has been terminated without permanent stabilization as is required in CGP Part 8.2 and City Ordinance 14-5-2-11. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days per CGP Part 2.2.14. In accordance with City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 has occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | NA
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action