## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | 6701 Tennyson St. NE
ESC File No. | E22E023 |  | Project Name: |  | Allaso High Desert | [5 empty] | NMR1003FW
NPDES Id. No. | NMR1005KR |  | Location: |  | 6701 Tennyson St. NE | [6 empty] | Joseph Aguilar <jaguilar@pavilionconstruction.com>
2024-06-06 |  | Owner |  |  |  | Contractor |  |  |  |  | Titan, HD, LLC
Operator |  | Titan HD, LLC |  |  |  | Pavilion Construction |  |  |  |  | 505-998-0163 | Max Saiz <msaiz@pavilionconstruction.com>
Contact name & title |  | Josh Rogers |  |  |  | Clayton Griffin |  |  |  |  | jrogers@titan-development.com
e-mail |  | jrogers@titan-development.com |  |  |  | cgriffin@pavilionconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 410-5301 |  |  |  |  | Bob Kearney
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  | bkearney@titan-development.com |  | Rain
Construction Phase: | [12 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 85 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-04-01 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP Map is out-of-date as it does not show the staging areas on the neighboring properties to the west and south in violation of CGP Part 7.4.1. The specific individuals for the stormwater team have not been identified in violation of CGP Part 7.2.2. Required mitigation: You must modify your SWPPP, including the site map(s), within 7 days, whenever you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1. Identify the personnel (by name and position) that you have made part of the stormwater team, as well as their individual responsibilities, including which members are responsible for conducting inspections per 7.2.2. | [9 empty] | 2021-05-03
2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-12
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action