## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [9 empty] | 6701 Tennyson St. NE
ESC File No. | E22E023 |  | Project Name: |  | Allaso High Desert |  |  |  |  | NMR1003FW
NPDES Id. No. | NMR1003FW |  | Location: |  | 6701 Tennyson St. NE | [5 empty] | Joseph Aguilar <jaguilar@pavilionconstruction.com>
2021-05-28 |  | Owner |  |  |  | Contractor |  |  |  | Titan, HD, LLC
Operator |  | Titan HD, LLC |  |  |  | Pavilion Construction |  |  |  | 505-998-0163 | Max Saiz <msaiz@pavilionconstruction.com>
Contact name & title |  | Josh Rogers |  |  |  | Joseph Aguilar |  |  |  | jrogers@titan-development.com
e-mail |  | jrogers@titan-development.com |  |  |  | jaguilar@pavilionconstruction.com
Contact Phone # |  | 505-998-0163 | [7 empty] | Bob Kearney
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 1:45 PM-2:10 PM |  |  | bkearney@titan-development.com |  | Rain
Construction Phase: |  | earthwork, infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 86 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [8 empty] | 2021-04-28
1 | No posting of permit coverage. Post signage of NOI permit coverage in a location clear visible to the public. | [8 empty] | 2021-05-03
2 | Small section of silt fence at South entrance is not properly installed. Silt fence needs to cover the bottom of the fence to prevent sediment from exiting the site. | [8 empty] | 2021-05-31
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Superintendent(s) were gone and project trailer was locked.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action