## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | 6701 Tennyson St. NE
ESC File No. | E22E023 |  | Project Name: |  | Allaso High Desert | [5 empty] | NMR1003FW
NPDES Id. No. | NMR1005KR |  | Location: |  | 6701 Tennyson St. NE | [6 empty] | Joseph Aguilar <jaguilar@pavilionconstruction.com>
2023-04-26 |  | Owner |  |  |  | Contractor |  |  |  |  | Titan, HD, LLC
Operator |  | Titan HD, LLC |  |  |  | Pavilion Construction |  |  |  |  | 505-998-0163 | Max Saiz <msaiz@pavilionconstruction.com>
Contact name & title |  | Josh Rogers |  |  |  | Clayton Griffin |  |  |  |  | jrogers@titan-development.com
e-mail |  | jrogers@titan-development.com |  |  |  | cgriffin@pavilionconstruction.com
Contact Phone # |  | 505-998-0163 |  |  |  | 410-5301 |  |  |  |  | Bob Kearney
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  | bkearney@titan-development.com |  | Rain
Construction Phase: |  | 80% Paved 0% occupied and 0% stabilized | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 52 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | SWPPP not up-to-date (Old NOI and CGP, Certification not signed by operators). Provide current documents in the SWPPP. Update landscaping and SWPPP map per comments below. | [9 empty] | 2021-05-03
2 | Stabilization specifications are missing from the SWPPP. The SWPPP must include site-specific interim and permanent stabilization per CGP 9.6.1.c.i. 12. The Landscape Plan and Work Order sheets can be used to satisfy this requirementt and they should be included in the SWPPP. Provide a specification on the ESC Plan for any disturbed areas not covered by the Landscape Plan or Work Order sheets especially on the slopes east and west of the site and on the staging areas. Provide a specifications on the ESC Plan along with schedules for implementation per CGP 2.2.14 for areas not covered by the Landscape Plan. Label areas to be stabilized with landscape rock (all areas in the public ROW) on the map and show typical section and specifications. Label areas to be stabilized with vegetation and provide details and specifications. | [9 empty] | 2021-05-31
3 | SWPPP Map is not accurate and up-to-date, 1) property boundary not accurate, it should be on the property line. 2) Limits of disturbance must be shown and include disturbed porstion of the City right of way, the neighbors' property, and AMAFCA's property, including all staging areas 3) Silt fences should be located at limits of disturbance, 4) provide stabilization map(s).
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2023-04-20
Notes: | SWPPP in trailer south of site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action