## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Coors Village Tracts 3A and 3B
Location: |  | Coors and Western Trail
Site Contact Name & Agency |  | Warren |  |  |  | ESC File No. | F11E019A
|  | TLC |  |  |  | NPDES Id. No.
Inspection Date: |  | 2019-07-09 | Start/End Time: |  | 7:45/7:50 |  | continued from 7-8-19 2:00 PM
CoA Stormwater Inspector: |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  | curb and gutter, installing utilities | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No VTC for vehicles exiting off service road that is located west of new N-S road
Spoke with Warren. This is a temporary situation as they are excavating in the drive path to use
the VTC that is currently there. Told him he could switch to daily sweeping until the drive
path to the VTC is restored
Gave them until COB to remove the minor track-out. Went back out for an early morning inspection 7-9-19 7:45 AM.
Track-out was removed.
Yes
| Discharge off site? (Y/N) |  |  | No | [7 empty] | No
| Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2019-06-19
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Curtis Cherne PE, 505-924-3420
|  | ccherne@cabq.gov |  |  |  |  | 2019-07-09

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action