## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F11E019A |  | Project Name: |  | Ativo Senior Living
NPDES Id. No. | NMR1005ZI |  | Location: |  | 4500 Quaker Heights Pl NW
2024-12-02 |  | Owner |  |  |  | Contractor
Operator |  | Ativo Albuquerque, LLC |  |  |  | Bradbury Stamm Construction
Contact name & title |  | Ron Ziebart |  |  |  | Dennis Towne
e-mail |  | ziebart@linksseniordevelopment.com |  |  |  | dtowne@bradburystamm.com
Contact Phone # |  | 503-363-4636 |  |  |  | 505-681-5562
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | Verticals, landscaping | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-11-20
Notes:
The majority of this site has been stabilized by vertical structures, pavement, and/or landscaping.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action