## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F13E028A |  | Project Name: |  | Griegos Farms
NPDES Id. No. | NMR1005G7 |  | Location: |  | 1860 Griegos Rd NW
2024-06-06 |  | Owner |  |  |  | Contractor
Operator |  | Griegos Farms, LLC |  |  |  | Guzman Construction Solutions
Contact name & title |  | Jay Rembe |  |  |  | Tyler Richter
e-mail |  | rembe@rembedesign.com |  |  |  | tyler@guzmancs.com
Contact Phone # |  | 505-453-7164 |  |  |  | 505-452-0663
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 130pm |  |  |  | Rain
Construction Phase: |  | beginning verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-04-01 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Permit Coverage posting is not visible from the road in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5.
2 | The perimeter silt fence is in need of repair in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
3 | There was concrete washout on bare soil and not in the provided washout container in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation and do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-29
Notes:
Called contact to review SWPPP
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action