## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F13E028A |  | Project Name: |  | Griegos Farms
NPDES Id. No. | NMR1005G7 |  | Location: |  | 1860 Griegos Rd NW
2025-05-07 |  | Owner |  |  |  | Contractor
Operator |  | Griegos Farms, LLC |  |  |  | Guzman Construction Solutions
Contact name & title |  | Jay Rembe |  |  |  | Tyler Richter
e-mail |  | rembe@rembedesign.com |  |  |  | tyler@guzmancs.com
Contact Phone # |  | 505-453-7164 |  |  |  | 505-452-0663
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:15pm |  |  |  | Rain
Construction Phase: |  | Approximately half the structures are complete and stabilized | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 60 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP has not been certified by either operator (Griegos Farms, LLC or Guzman Construction Solutions) in violation of CGP Part 7.2.10. The self-inspection reports were not current in violation of CGP Part 4.7.3. Required mitigation: Your signatory must sign and date your SWPPP in accordance with Appendix G, Part G.11. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available during an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-02-19
Notes:
SWPPP in doc-box mounted on the back of posting. Trenches along the perimeter with block walls and basins throughout the site limit discharge from the site.
Previous violations for washout, BMPs, and posting have been mitigated.
A Delegation of Authority has not been completed by the Griegos Farms, LLC NOI certifier.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action