## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | E14E036A |  | Project Name: |  | Champion Xpress Car Wash
NPDES Id. No. | NMR10053G |  | Location: |  | 5307 4th St. NW
2023-07-05 |  | Owner |  |  |  | Contractor
Operator |  | VIA Real Estate, LLC |  |  |  | 7B Building and Development
Contact name & title |  | Jordan Merchant |  |  |  | Kordell Doshier
e-mail |  | jordan@7bdev.com |  |  |  | kordell@7bdev.com
Contact Phone # |  | 806-368-7843 |  |  |  | 806-368-7843
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 3pm |  |  |  | Rain
Construction Phase: |  | Foundations and utility install; sidewalk demo | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 100 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The latest inspection reports were not available during the inspection, the most current self inspection report in the SWPPP was dated 3/21/2023 and the inspection reports were missing the proper signatures. The Delegation of Authority page does not have an individual or position title designated to sign inspection reports. Per CGP Section 4.7.3, you must keep a copy of all inspection reports at the site or an easily accesible location, so that it can be made immediately available at the time of inspection. Section 4.7.2 of the CGP requires that inspection reports be signed by the operator's signatory in accordance with Appendix G, Part G.11. Appendix G, Part G.11.2.2 states that a person is a duly authorized representative if the authorization specifies either an individual or a position having responsibility for the overall operation of the facility.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-03-21
Notes:
Previous site inspections performed by the City have found the SWPPP to be out of date and lacking current (up-to-date) self inspection reports
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action