## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F14E036A |  | Project Name: |  | Champion Xpress Car Wash
NPDES Id. No. | missing |  | Location: |  | 5307 4th St. NW | [5 empty] | Pete Jacobsen | Stormwater Solutions
2022-08-23 |  | Owner |  |  |  | Contractor |  |  |  |  | Klinger | Stephanie Maestas
Operator |  | Martinez Property Holdings, LLC |  |  |  | 7B Building and Development |  |  |  |  | 505-228-8567
Contact name & title |  | 4611 Rio Grande Ln NW |  |  |  | Jordan Merchant |  |  |  |  | petej@klingerllc.com
e-mail |  | Los Ranchos De Albuquerque |  |  |  | jordan@7bdev.com
Contact Phone # |  | NM 87101 5503 |  |  |  | 806-368-7843
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 4pm |  |  |  |  | Rain
Construction Phase: |  | grading | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 83 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-06-28 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | NPDES Permit coverage is missing. This site is part of a common plan of development that requires permit coverage but land disturbing activities started before permit coverage was obtained. Obtain permit coverage from the EPA and submit the property owner's NOI and ESC Plan to the City for review and approval. | [9 empty] | 2021-05-03
2 | Posting of permit coverage was missing. Post signage of NOI permit coverage in a location clearly visible to the public CGP1.5. | [9 empty] | 2021-05-31
3 | The up-to-date SWPPP was not available onsite. The SWPPP must include current self-inspection reports and an accurate SWPPP map showing current BMPs and current area of disturbance per CGP 7.2.1 and 7.2.4.
4 | Inactive areas must be stabilized within 14 days per CGP2.2.14.
5 | BMPs were missing. BMPs must be constructed within 7 days per CGP 5.2.1.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes:
About 0.6 acres are covered by bare dirt with some rock/gravel thinly and irregularly scattered. Demolition of a building and parking lot exposed the dirt in 2019.
This lot and the lot to the south are part of a common plan of development. The grading plan and building permit for Champion Xpress Car Wash was approved by Hydrology on 6/27/2022.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action