## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F14E036A |  | Project Name: |  | Champion Xpress Car Wash
NPDES Id. No. | NMR10053G |  | Location: |  | 5307 4th St. NW | [5 empty] | Pete Jacobsen | Stormwater Solutions
2022-11-14 |  | Owner |  |  |  | Contractor NMR10053G |  |  |  |  | Klinger | Stephanie Maestas
Operator |  | VIA Real Estate, LLC |  |  |  | 7B Building and Development |  |  |  |  | 505-228-8567
Contact name & title |  | Jordan Merchant |  |  |  | Kordell Doshier |  |  |  |  | petej@klingerllc.com
e-mail |  | jordan@7bdev.com |  |  |  | kordell@7bdev.com
Contact Phone # |  | 806-368-7843 |  |  |  | 806-368-7843
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11am |  |  |  |  | Rain
Construction Phase: |  | grading | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-10-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP was available onsite but it wasn't up-to-date. See attached SWPPP checklist. | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
3
4
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2022-11-12
Notes:
The original NOI (NMR10053G) for 7 B Building and Development was signed by Jordan Merchant on 9/15/22 which was changed to an NOI for Via Real Estate LLC and certified by Jordan Merchant on 10/17/22. Both list Kordell Doshier as the point of cantact. A Deligation of Authority was emailed but incorectly signed by Vincent Paul, vincent@7bdev.com 505-401-0615, instead of Jordan Merchant.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action