## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR1003QT/NMR1003SI
ESC File No. | F14E076 |  | Project Name: |  | Bosque Escondido | [5 empty] | Montano Family Homes, LLC/Troyer Homes, LLC - Nathan Troyer/Tim Nisley
NPDES Id. No. | NMR1003QT/NMR1003SI |  | Location: |  | 712 Montano Rd. NE | [5 empty] | Bosque Escondido; 712 Montano Rd. NW
2021-06-08 |  | Owner |  |  |  | Contractor |  |  |  |  | Nathan 505-385-6736/ Tim 505-328-8848
Operator |  | Montano Family Homes, LLC. |  |  |  | Troyer Homes, LLC |  |  |  |  | troyerhomesllc@gmail.com; tim@101prop.com
Contact name & title |  | Nathan Troyer |  |  |  | Tim Nisley
e-mail |  | troyerhomesllc@gmail.com |  |  |  | tim@101prop.com
Contact Phone # |  | 505-385-6736 |  |  |  | 505-328-8848
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:45 PM-2:50 PM |  |  |  | Rain
Construction Phase: |  | Pre-construction, BMPs | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | None observed. | [9 empty] | 2021-05-03
2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-05-24
Notes: | Construction and silt fence has been installed. No activity on site during this inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action