## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [12 empty] | Mavrik - 19054 ABQ NM; 3601 Montgomery Blvd.
ESC File No. | F16E001A |  | Project Name: |  | Maverik - 19054 ABQ NM | [5 empty] | Lance Dunkley
NPDES Id. No. | NMR10032O |  | Location: |  | 3601 Montgomery Blvd. NE | [5 empty] | 801-683-3960 |  | Enterprise Builders
2021-05-20 |  | Owner |  |  |  | Contractor | [6 empty] | David Lundsten
Operator |  | Maverik |  |  |  | Enterprise Builders | [6 empty] | 505-452-7639
Contact name & title |  | Lance Dunkley |  |  |  | David Lundsten |  |  |  |  | tim Slatunas |  | dlundsten@ebnm.com
e-mail |  | lance.dunkley@maverik.com |  |  |  | dlundsten@ebnm.com
Contact Phone # |  | 801-683-3960 |  |  |  | 505-452-7639
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 3:15 PM/3:35 PM |  |  |  | Rain
Construction Phase: |  | Building Construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 88 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Inspection reports not in SWPPP. Maintain copies of the self-inspection reports on site in the SWPPP (CGP 4.7.3). Self-inspection reports shall be signed by an authorized representative per CGP 4.7.2 (Appendix I, section I.11.2 | [9 empty] | 2021-05-03 | 1. Self-inspection reports must be signed per CGP Appendix I, Section I.11.2
2 | [11 empty] | 1. Maintain a copy of the self-inspection reports on site (CGP 4.7.3). Self-inspection reports must be signed by an authorized representative per CGP 4.7.2 (Appendix I, Section I.11.2).
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-05-19
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action