## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F16E003E1 |  | Project Name: |  | Top Golf- ABQ
NPDES Id. No. | NMR1001XF |  | Location: |  | 1600 Desert Surf Loop | [5 empty] | 'jeff@woodsonia.net'
2021-06-24 |  | Owner |  |  |  | Contractor
Operator |  | Woodsonia Real Estate, Inc. |  |  |  | Tierra West, LLC |  |  |  |  | 'Brad Frosch' <bfrosch@tierrawestllc.com>
Contact name & title |  | Jeff Elliot |  |  |  | Brad Frosch
e-mail |  | jeff@woodsonia.net |  |  |  | bfrosch@tierrawestllc.com |  |  |  |  | 'Ron Bohannan' <rrb@tierrawestllc.com>
Contact Phone # |  | 402-513-9003
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:15 PM-2:35 PM |  |  |  | Rain
Construction Phase: |  | Stabilization | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | rain |  | Temperature: ~ |  |  | 86 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-31 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Silt fence is down around pond. Repair and maintain silt fence. | [9 empty] | 2021-05-03
2 | Maintain stabilization controls on the pond. | [9 empty] | 2021-05-31
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2021-03-09
Notes: | Hydro mulch has been applied to the pond. Some areas may need to be mulched again. The
remaining areas around the site have been stabilized.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action