## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [13 empty] | NM JATC Building Addition - 4501 Montbel Pl. NE
ESC File No. | F16E011 |  | Project Name: |  | NM JATC Building Addition | [5 empty] | tim Slatunas
NPDES Id. No. | NMR1002ZB |  | Location: |  | 4501 Montbel Pl. NE | [8 empty] | Charles Humiston - NM Joint Apprenticeship Training Committee For the Electrial Industry
2021-05-20 |  | Owner |  |  |  | Contractor |  |  |  |  | Ed Fuller | Summit Construction |  | 505-341-4444
Operator |  | NM JATC for the Electrical Industry |  |  |  | Summit Construction |  |  |  |  | ed@summitconstr.com |  |  | director@nmjatc.org
Contact name & title |  | Charles Humiston |  |  |  | Ed Fuller
e-mail |  | director@nmjatc.org |  |  |  | ed@summitconstr.com |  |  |  |  | Travis Porter |  |  |  | NMR1002ZB
Contact Phone # |  | 505-341-4444 |  |  |  | 505-239-4824 |  |  |  |  | Summit Project Manager
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:45 PM/3:05 PM |  |  | 505-842-8113 |  | Rain
Construction Phase: |  | Final Stabilization | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 86 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No posting of NOI. Re-post signage of NOI permit coverage in a location clearly visible to the public. | [9 empty] | 2021-05-03
2 | Re-establish permiter BMPs for erosion and sediment control.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | none on file
Notes: | Per Ed Fuller, hydro-seed was applied 3 weeks ago across the site. Hydro-mulch was
applied today. They removed their posting of permit coverage, and I directed them to re-post it.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action