## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Tru by Hilton
Location: |  | 4949 Jefferson NE
Site Contact Name & Agency |  | Ken Moore, Wright Hospitality |  |  |  | ESC File No. | F17E044C
|  | ken@wrighthospitality.com |  |  |  | NPDES Id. No. | NMR10021J
Inspection Date: |  | 2019-10-24 | Start/End Time: |  | 8:25/8:40
CoA Stormwater Inspector: |  |  | Doug Hughes
Construction Phase: |  | vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-10-04 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Remove and properly dispose of all offsite sediment and prevent sediment from leaving the site in the future. | [10 empty] | Post a notice of your permit coverage
2 | Direct wash water from stucco, paint and concrete into a leak-proof container or lined pit . | [10 empty] | self inspection reports required every 14 days and after each rain>0.25". Please e-mail
3 | Keep construction and domestic waste in acceptable containers. | [10 empty] | Maintain stormwater controls (BMPs). Silt fence needs repaired east side.
4 | Keep construction and domestic waste container lids closed when not in use. | [10 empty] | Keep construction and domestic waste container lids closed when not in use.
Yes
1.1 | Discharge off site? (Y/N) |  |  | yes | [7 empty] | No
5 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2019-10-09
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action