## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F17E044C |  | Project Name: |  | TRU by Hilton Hotel
NPDES Id. No. | NMR10021J; NMR10021K; NMR1002QU |  | Location: |  | 4949 Jefferson St.
2021-04-15 |  | Owner |  |  |  | Contractor
Operator |  | Hanuman Corporation |  |  |  | Wright Hospitality
Contact name & title |  | Sam Patel |  |  |  | Ken Moore
e-mail |  | Taurus5468@gmail.com |  |  |  | ken@wrighthospitality.com
Contact Phone # |  | 505-797-9347
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 1:50 PM/2:00 PM |  |  | Rain
Construction Phase: |  | Stabilization | [7 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-02-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [9 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Final stabilization does not appear to be completed on right of way.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no |  |  |  |  | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | Site is completed and open for business.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action