## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F21E028 |  | Project Name: |  | La Vida Llena
NPDES Id. No. | NMR1002G1/NMR1002PF |  | Location: |  | 10501 La Grima De Oro | [6 empty] | orodriguez@bradburystamm.com
2021-05-04 |  | Owner |  |  |  | Contractor
Operator |  | La Vida Llena |  |  |  | Bradbury Stamm | [5 empty] | Tim Slatunas
Contact name & title |  | Joe Gomez |  |  |  | Oscar Rodriguez
e-mail |  | jgomez@lavidallena.com |  |  |  | orodriguez@bradburystamm.com
Contact Phone # |  | 505-293-4001 |  |  |  | 505-332-2350
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:10 PM/2:00 PM |  |  |  |  | Rain
Construction Phase: |  | Home construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 69 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Trackout at site entrances. Sweep and remove trackout daily. | [9 empty] | 2021-05-03
2 | Area behind the North wall appears to be eroding. Provide stabilization controls to prevent further erosion.
3 | No sediment control around dirt pile at NW side of the street. Dirt is going on the sidewalk. Place sediment control BMP to prevent sediment from entering the street/sidewalk.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-06-05
Notes: | Heavy rains the previous day caused ponding of water. Crew was dewatering and
discharging water out the Southwest construction entrance. The water collects in a pond at the far
Southwest corner of the complex. SWPPP is kept on site. Self-inspection reports are kept
electronically.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action