## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | F21E081 |  | Project Name: |  | Guardian Storage
NPDES Id. No. | NMR10022Q |  | Location: |  | 4909 Juan Tabo Blvd. NE
2021-05-04 |  | Owner |  |  |  | Contractor
Operator |  | Guardian Storage IV, LLC.
Contact name & title |  | Paul Hedges |  |  |  | Dawson Hedges
e-mail |  | pdhedges@hotmail.com |  |  |  | hedges72@comcast.net
Contact Phone # |  | 505-450-6385
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 2:05 PM/2:20 PM |  |  |  | Rain
Construction Phase: |  | Building construction/flatwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 72 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Significant erosion in pond area at SW corner of site. Maintain erosion and sediment controls to prevent any sediment from exiting the site. Remove sediment from the jogging path. | [9 empty] | 2021-05-03
2 | Washout on the ground. Direct wash water from concrete, paint, and stucco into a leak-proof container per CGP 2.3.4. Remove and dispose of hardened concrete with other waste per CGP 2.2.3.
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-01
Notes: | Spoke with Dawson. Self-inspection reports are kept electronically. SWPPP is at the
office. Project is about 95% completed, with flatwork expected to be completed next week.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action