## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | 3050 Painted Rock
Location: |  |  | 3050 Painted Rock
Site Contact Name & Agency |  |  | Robert Schultis - All-Rite Const. |  |  | ESC File No. | G10E029D
[6 empty] | NPDES Id. No. | NMLEWA301
Inspection Date: |  |  |  | Start/End Time:
CoA Stormwater Inspector: |  |  |  | Timothy Sims
Construction Phase: |  |  | grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  | Temperature: ~ |  |  | 60* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [12 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Please provide Stormwater Quality Approval and post in view to the public at site.
2 | Dirt Ramp onto BoB McCannon Parkway requires removal and an acceptable access ramp is
required.
3 | Concrete washout not in acceptable container.
4 | Please provide latest SWPPP self-inspection report.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | requested | Latest report Date: |  | not on file
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
tsims@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action