## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E058 |  | Project Name: |  | Sequoia Apartments
NPDES Id. No. | NMR1005BW |  | Location: |  | 5130 Sequoia Rd. NW
2025-09-08 |  | Owner |  |  |  | Contractor
Operator |  | Nouri Apartments |  |  |  | J&S Development Inc.
Contact name & title |  | Esmail Haidari |  |  |  | Jose Rodriguez
e-mail |  | EsmailHaidari060@gmail.com |  |  |  | Rodriguez3003@hotmail.com
Contact Phone # |  | 505-250-6088 |  |  |  | 505-440-5104
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1pm |  |  |  | Rain
Construction Phase: |  | Verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-09-06 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP is not current - J & S Development Inc is not identified in the SWPPP in violation of CGP Part 7.2.1. The stormwater team has not been identified in the SWPPP in violation of CGP Part 7.2.2. The NOI for Nouri Apartments LLC is not the certified copy in violation of CGP Part 7.2.11. Required mitigation: Include a list of all other operators who will be engaged in construction activities at the site, and the areas of the site over which each operator has control per CGP Part 7.2.1. Identify the personnel (by name and position) that you have made part of the stormwater team pursuant to CGP Part 6.1, as well as their individual responsibilities (design, installation, maintenance, and/or repair of stormwater controls; conducting inspections; taking corrective actions) per CGP Part 7.2.2. You must include a copy of your NOI submitted to the EPA along with any correspondence exchanged between you and the EPA related to coverage per CGP Part 7.2.11.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-08-22
Notes:
The SWPPP is in a mailbox attached to the posting sign.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action