## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E058 |  | Project Name: |  | Sequoia Apartments
NPDES Id. No. | NMR1005BW |  | Location: |  | 5130 Sequoia Rd. NW
2026-01-02 |  | Owner |  |  |  | Contractor
Operator |  | Nouri Apartments |  |  |  | J&S Development Inc.
Contact name & title |  | Esmail Haidari |  |  |  | Jose Rodriguez
e-mail |  | EsmailHaidari060@gmail.com |  |  |  | Rodriguez3003@hotmail.com
Contact Phone # |  | 505-250-6088 |  |  |  | 505-440-5104
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9:30am |  |  |  | Rain
Construction Phase: |  | Interiors | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | BMPs - The stormwater quality ponds shown on the approved ESC Plan have not been installed in violation of CGP Part 2.1.3. Required mitigation: Complete installation of stormwater controls by the time each phase of construction activities has begun per CGP Part 2.1.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-11-14
Notes:
The SWPPP is in a mailbox attached to the posting sign.
Most of the site has been stabilized by a gravel base course.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action