## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E058 |  | Project Name: |  | Sequoia Apartments
NPDES Id. No. | NMR1005BW |  | Location: |  | 5130 Sequoia Rd. NW
2024-05-05 |  | Owner |  |  |  | Contractor
Operator |  | Nouri Apartments |  |  |  | J&S Development Inc.
Contact name & title |  | Esmail Haidari |  |  |  | Jose Rodriguez
e-mail |  | EsmailHaidari060@gmail.com |  |  |  | Rodriguez3003@hotmail.com
Contact Phone # |  | 505-250-6088 |  |  |  | 505-440-5104
COA Inspector |  | Doug Hughes | [9 empty] | Rain
Construction Phase: |  | Slab and framing | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
4 | The SWPPP and self-inspection reports were not available on-site during the inspection in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. No personnel were onsite, and the location of the SWPPP was not posted on a sign at the entrance. Required Mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3, and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site per CGP 7.3.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | ?
Notes:
The SWPPP was not on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action