## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E067 |  | Project Name: |  | Oxbow Center
NPDES Id. No. | NMR1006GI |  | Location: |  | Coors Blvd and St Josephs Rd NW
2024-12-19 |  | Owner |  |  |  | Contractor
Operator |  | Red Shamrock 12, LLC |  |  |  | Franklin's Earthmoving Inc.
Contact name & title |  | Joshua Skarsgard |  |  |  | Gus Harbaugh
e-mail |  | josh@retailsouthwest.com |  |  |  | gus.harbaugh@feinm.com
Contact Phone # |  | 505-998-9093 |  |  |  | 505-975-2864
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:45pm |  |  | Rain
Construction Phase: |  | graded, inactive | [8 empty] | Clear/ Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were unavailable at the time of the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a current copy of your SWPPP and all self-inspection reports at the site or at an easily accessible location so that they can be made available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-12-18
Notes:
Graded and some curbs installed; inactive
QR Code for SWPPP and reports, but nothing to view "same as paper".
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action