## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E067 |  | Project Name: |  | Oxbow Center
NPDES Id. No. | NMR1006GI |  | Location: |  | Coors Blvd and St Josephs Rd NW
2025-05-05 |  | Owner |  |  |  | Contractor
Operator |  | Red Shamrock 12, LLC |  |  |  | Franklin's Earthmoving Inc.
Contact name & title |  | Joshua Skarsgard |  |  |  | Gus Harbaugh
e-mail |  | josh@retailsouthwest.com |  |  |  | gus.harbaugh@feinm.com
Contact Phone # |  | 505-998-9093 |  |  |  | 505-975-2864
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 9:45pm |  |  |  | Rain
Construction Phase: |  | grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | none
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | OK | Latest report Date: |  | 2025-04-25
Notes: | The SWPPP was in a lockbox on the back of the sign.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action