## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E067F |  | Project Name: |  | Olive Garden on Coors
NPDES Id. No. | NMR1006od |  | Location: |  | 3823 Coors Boulevard NW
2024-10-21 |  | Owner |  |  |  | Contractor
Operator |  | Olive Garden Holdings, LLC |  |  |  | Tangelwood Construction
Contact name & title |  | Robert Ricketts |  |  |  | Todd Granath
e-mail |  | rricketts@darden.com |  |  |  | toddg@tanglewoodconstructionnm.com
Contact Phone # |  | 407-245-5183 |  |  |  | 505-668-0495
COA Inspector |  | James Hughes |  |  |  | Time |  | 10AM |  |  |  | Rain
Construction Phase: |  | overexavation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2029-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting - CGP coverage was not posted so it is visible from the public road nearest to the active part of the construction site, using a font large enough to be readily viewed from a public right-of-way in violation of CGP 1.5. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
2 | SWPPP - The required notice of the SWPPP location wasn't posted in violation of CGP7.3, and the SWPPP and self-inspection reports were not available in Violation of CGP 7.3, City Ordinance § 14-5-2-11(C)(1), and CGP 4.7.3. Required Mitigation: The SWPPP, including the SWPPP Map, Self-Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3.
3 | BMPs - Perimeter Silt Fence (SF) was not installed correctly and the Construction Exit (CE) was missing in violation of CGP 2.2.3 & 2.2.4 The SF wasn't embedded on the low side of the site and there was a gate that will not be allowed along coors. The installation of the stormwater controls wasn't complete before the beginning of Construction Activities in Violation of CGP 2.1.3. Required mitigation: Embed the silt fence across the low itional stormwater controls, ponds, berm, and CE must be designed and installed in accordance with CGP 2.1.4 no later than seven (7) calendar days from the time of discovery per CGP 5.2.1.
4 | Stabilization—About half of the perennial vegetation was removed from this site in a 35' wide strip around the edges plus about 0.25-acre pad site in the south 80 of the site as part of the subdivision development that started in late 2022, and this site was still under permit coverage when Goodwill purchased it on 12/29/2023. The edges were Hydromulched in mid-2023 but didn't grow significant perennial vegetation, and the mulch had large bare spots before the end of 2023. The pad had thin spotty gravel cover in Aug 2024. At the time of the inspection on 10/21/24, the previously disturbed area had been scraped, moving vegetation and trash into piles, but the area of native vegetation remained undisturbed in the center third of the lot. Required Mitigation: Stabilize the disturbed areas that remain inactive for 14 days or more per CGP 2.2.14.c.i. Measures must be initiated within 14 days and completed no later than 14 days per CGP 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | none
Notes: | This inspection was conducted 2 days after a 0.36" rain but no discharge.
Robert Ricketts said that Olive Garden is just the Lessee and isn't in control of the property yet. He said that the Lessor is still in control of the site. I pointed out that the contracto on site was Tanglewood Construction and he said that he wasn't sure who if that is his contractor or not. However the doesn't have any control over the property yet, and said that the site is under control of the the owner
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action