## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E067D |  | Project Name: |  | Raising Cane's #1156
NPDES Id. No. | NMR1006ET |  | Location: |  | St Joseph's Dr NW and Coors Blvd NW
2025-08-26 |  | Owner |  |  |  | Contractor
Operator |  | Raising Cane's Restaurants, LLC |  |  |  | Embree Construction Group, Inc.
Contact name & title |  | Robert Montgomery |  |  |  | Andrew DeLeon
e-mail |  | rmontgomery@rasingcanes.com |  |  |  | adeleon@embreegroup.com
Contact Phone # |  | 972-769-3357 |  |  |  | 512-630-8025
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2:45pm |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-07-03 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | BMPs - The construction exit allows for sediment track-out in violation of CGP Parts 2.1.2 and 2.2.4. Required mitigation: Install all stormwater controls in accordance with good engineering practices per CGP Part 2.1.2. Implement additional track-out controls as necessary to ensure that sediment removal occurs prior to vehicle exit per CGP Part 2.2.4. Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which the track-out occurs.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
Construction started less than two weeks prior to the City inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action