## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E067F |  | Project Name: |  | Olive Garden on Coors
NPDES Id. No. | NMR1006od |  | Location: |  | 3823 Coors Boulevard NW
2024-10-21 |  | Owner |  |  |  | Contractor
Operator |  | Olive Garden Holdings, LLC |  |  |  | Tangelwood Construction
Contact name & title |  | Robert Ricketts |  |  |  | Todd Granath
e-mail |  | rricketts@darden.com |  |  |  | toddg@tanglewoodconstructionnm.com
Contact Phone # |  | 407-245-5183 |  |  |  | 505-668-0495
COA Inspector |  | James Hughes |  |  |  | Time |  | 10AM |  |  |  | Rain
Construction Phase: |  | overexavation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? | [5 empty] | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2029-10-19 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Not started yet
2
3
4
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | no
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | none
Notes: | This inspection was conducted 2 days after a 0.36" rain but no discharge.
Robert Ricketts said that Olive Garden is just the Lessee and isn't in control of the property yet. He said that the Lessor is still in control of the site. I pointed out that the contractor on site was Tanglewood Construction, and Robert said that he wasn't sure if that was his contractor or not; however, he doesn't have any control over the property yet and said that the site is under the control of the owner. Upon further investigation, I found that the disturbed area was on the 7 Brews site north of the Olive Garden site, and Olive Garden construction had not started yet.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action